## Product Backlog
Product Backlog
Backlog ID | User Story
101 | As a Student I Want………………..
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120

## Sprint Backlogs
Sprint 01
Product Backlog ID | Sprint Backlog ID | User Story
101 | 1001 | Data Collection
| 1002 | Feature Selection
| 1003 | Feature Engineering
| 1004 | Data Encodeing
Sprint 02
Product Backlog ID | Sprint Backlog ID | User Story
102 | 2001 | Data Collection
| 2002 | Feature Selection
| 2003 | Feature Engineering
| 2004 | Data Encoding
Sprint 03
Product Backlog ID | Sprint Backlog ID | User Story
103 | 3001 | Model Selection
| 3002 | Runs Prediction
| 3003 | Testing
| 3004 | Dismissal Prediction
| 3005 | Testing
| 3006 | Dismissal Rate Prediction
| 3007 | Testing
| 3008 | Strike rate Prediction
| 3009 | Testing
| 3010 | Model Comparison
| 3011 | Backend Integration
Sprint 04
Product Backlog ID | Sprint Backlog ID | User Story
104 | 4001 | Backend API for Dynamic Dropdowns
| 4002 | Frontend for Dynamic Dropdowns
| 4003 | Backend API for AJAX Predictions
| 4004 | Frontend for AJAX Predictions
| 4005 | Implement Animated Results
| 4006 | UI Polishing & Styling
Sprint 05
Product Backlog ID | Sprint Backlog ID | User Story
Sprint 06
Product Backlog ID | Sprint Backlog ID | User Story

## Sprint_01 BurnDown Chart
SPRINT 1 BURNDOWN CHART
Backlog_ID | User Stories/Sprint Backlog | Initial Estimate | 2010-07-01 | 2011-07-01 | 2012-07-01 | 2013-07-01 | 2014-07-01 | 2015-07-01 | 2016-07-01 | 2017-07-01 | 2018-07-01 | 2019-07-01
|  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10
1001 | Problem Definition | 4 | 2010-07-01: 1; 2011-07-01: 2; 2012-07-01: 1
1002 | Literature Research | 3 | bar: 2014-07-01 to 2016-07-01
1003 | Project Planning | 3 | 2016-07-01: 1; 2017-07-01: 1; 2018-07-01: 1; 2019-07-01: 0
Remaining Effort |  | 10 | 9 | 7 | 6 | 6 | 5 | 4 | 2 | 1 | 0 | 0
Ideal Trend |  | 10 | 9 | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1 | 0

## Sprint_02 BurnDown Chart
SPRINT 2 BURNDOWN CHART
Backlog_ID | User Stories/Sprint Backlog | Initial Estimate | 2025-07-01 | 2026-07-01 | 2027-07-01 | 2028-07-01 | 2029-07-01 | 2030-07-01 | 2001-08-01 | 2002-08-01 | 2003-08-01 | 2004-08-01
|  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10
2001 | Data Collection | Day 0: 8; Day 1: 3; Day 2: 2; Day 3: 2; Day 4: 1
2002 | Feature Selection | Day 0: 5; Day 4: 2; Day 5: 2; Day 6: 1
2003 | Feature Engineering | Day 0: 4; Day 6: 1; Day 7: 2; Day 8: 1
2004 | Data Encoding | Day 0: 3; Day 9: 2; Day 10: 1
Remaining Effort |  | 20 | 17 | 15 | 13 | 10 | 8 | 6 | 4 | 3 | 1 | 0
Ideal Trend |  | 20 | 18 | 16 | 14 | 12 | 10 | 8 | 6 | 4 | 2 | 0

## Sprint_03 BurnDown Chart
SPRINT 3 BURNDOWN CHART
Backlog_ID | User Stories/Sprint Backlog | Initial Estimate | 2007-08-01 | 2008-08-01 | 2009-08-01 | 2010-08-01 | 2011-08-01 | 2012-08-01 | 2013-08-01 | 2014-08-01 | 2015-08-01 | 2016-08-01 | 2017-08-01 | 2018-08-01 | 2019-08-01 | 2020-08-01 | 2021-08-01 | 2022-08-01
|  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15 | Day 16
3001 | Model Selection | 2 | bar: 2007-08-01 to 2008-08-01
3002 | Runs Prediction | 4 | 2008-08-01: 2; 2009-08-01: 2
3003 | Dismissal Prediction | 4 | 2010-08-01: 2; 2011-08-01: 1; 2012-08-01: 1
3004 | Dismissal Rate Prediction | 4 | 2013-08-01: 3; 2014-08-01: 1
3005 | Strike rate Prediction | 4 | 2015-08-01: 2; 2016-08-01: 1; 2017-08-01: 1
3006 | Testing | 4 | bar: 2010-08-01; 2013-08-01; 2015-08-01; 2017-08-01
3007 | Model Comparison | 2 | bar: 2018-08-01 to 2019-08-01
3008 | Backend Integration | 8 | 2019-08-01: 1; 2020-08-01: 3; 2021-08-01: 3; 2022-08-01: 1
Remaining Effort |  | 32 | 31 | 28 | 26 | 23 | 22 | 21 | 17 | 16 | 13 | 12 | 10 | 9 | 7 | 4 | 1 | 0
Ideal Trend |  | 32 | 30 | 28 | 26 | 24 | 22 | 20 | 18 | 16 | 14 | 12 | 10 | 8 | 6 | 4 | 2 | 0

## Sprint_04 BurnDown Chart
SPRINT 4 BURNDOWN CHART
Backlog_ID | User Stories/Sprint Backlog | Initial Estimate | 2011-09-01 | 2012-09-01 | 2013-09-01 | 2014-09-01 | 2015-09-01 | 2016-09-01 | 2017-09-01 | 2018-09-01 | 2019-09-01
|  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9
4001 | UI Planing | 3 | 2011-09-01: 1; 2012-09-01: 2
4002 | Backend for Dynamic Dropdowns | 2 | 2013-09-01: 2
4003 | Frontend for Dynamic Dropdowns | 2 | bar: 2013-09-01 to 2014-09-01
4004 | Backend for Predictions | 2 | 2015-09-01: 2
4005 | Frontend for Predictions | 2 | bar: 2015-09-01 to 2016-09-01
4006 | Implement Animated Results | 2 | bar: 2016-09-01 to 2017-09-01
4007 | UI Polishing & Styling | 5 | 2017-09-01: 2; 2018-09-01: 2; 2019-09-01: 1
Remaining Effort |  | 18 | 17 | 15 | 12 | 11 | 8 | 6 | 3 | 1 | 0
Ideal Trend |  | 18 | 16 | 14 | 12 | 10 | 8 | 6 | 4 | 2 | 0